## Sheet1
Overall Progress: 0%
Id | Name | Start | Due | Summarise | - | - | - | - | - | - | - | - | - | - | 24/06/2024 | 25/06/2024 | 26/06/2024 | 27/06/2024 | 28/06/2024 | 29/06/2024 | 30/06/2024 | 01/07/2024 | 02/07/2024 | 03/07/2024 | 04/07/2024 | 05/07/2024 | 06/07/2024 | 07/07/2024 | 08/07/2024 | 09/07/2024 | 10/07/2024 | 11/07/2024 | 12/07/2024 | 13/07/2024 | 14/07/2024 | 15/07/2024 | 16/07/2024 | 17/07/2024 | 18/07/2024 | 19/07/2024 | 20/07/2024 | 21/07/2024 | 22/07/2024 | 23/07/2024 | 24/07/2024 | 25/07/2024 | 26/07/2024 | 27/07/2024 | 28/07/2024 | 29/07/2024 | 30/07/2024 | 31/07/2024 | 01/08/2024 | 02/08/2024 | 03/08/2024 | 04/08/2024 | 05/08/2024 | 06/08/2024 | 07/08/2024 | 08/08/2024 | 09/08/2024 | 10/08/2024 | 11/08/2024 | 12/08/2024 | 13/08/2024 | 14/08/2024 | 15/08/2024 | 16/08/2024 | 17/08/2024 | 18/08/2024
1 | Week 1: 24/06/24-30/06/24 | 24/06/2024 | 30/06/2024 | 5
1.1 | Browsing for articles in related areas | 24/06/2024 | 30/06/2024 | 5
1.2 | Literature review on international currency fluctuations | 24/06/2024 | 30/06/2024 | 5
1.3 | Literature review on related economic theories | 24/06/2024 | 30/06/2024 | 5
1.4 | Browsing for valid sites with historical currency exchange datasets | 25/06/2024 | 29/06/2024 | 4
1.5 | Downloading related datasets | 25/06/2024 | 30/06/2024 | 4
1.6 | Refine research questions and hypotheses. | 25/06/2024 | 27/06/2024 | 3
1.7 | Initial project structure or outline + literature review draft | 28/06/2024 | 30/06/2024 | 1
1.8 | Initial Bibliography | 29/06/2024 | 30/06/2024 | -
2 | Week 2: 29/06/24-7/07/24 | 29/06/2024 | 07/07/2024 | 5
2.1 | Making edits to Chapter 1 and Literature review | 29/06/2024 | 07/07/2024 | 5
2.2 | Data collection from HESA and SFC | 29/06/2024 | 05/07/2024 | 5
2.3 | Data collection from IMF and World Bank | 29/06/2024 | 05/07/2024 | 5
2.4 | Data collection from University Websites | 01/07/2024 | 07/07/2024 | 5
2.5 | Data collection from Oanda and Investing.co.uk | 01/07/2024 | 07/07/2024 | 5
2.6 | Arranging of raw data in relevant folders | 01/07/2024 | 07/07/2024 | 5
3 | Week 3: 8/07/24 - 14/07/24 | 08/07/2024 | 14/07/2024 | 5
3.1 | Addressing missing values | 08/07/2024 | 14/07/2024 | 5
3.2 | Standardising variables | 08/07/2024 | 14/07/2024 | 5
3.3 | Removing irrelevant or duplicate data | 08/07/2024 | 10/07/2024 | 3
3.4 | Addressing inconsistencies | 08/07/2024 | 14/07/2024 | 5
3.5 | Addressing outliers | 08/07/2024 | 11/07/2024 | 4
3.6 | Generate clean and processed dataset for analysis | 14/07/2024 | 14/07/2024 | 1
4 | Week 4: 15/07/24-21/07/24 | 15/07/2024 | 21/07/2024 | 5
4.1 | Visualise distributions | 15/07/2024 | 19/07/2024 | 5
4.2 | Identify initial patterns | 15/07/2024 | 20/07/2024 | 5
4.3 | Calculate descriptive statistics | 16/07/2024 | 20/07/2024 | 4
4.4 | Identify correlations | 17/07/2024 | 20/07/2024 | 3
4.5 | Add relevant statistical data to other report chapters | 21/07/2024 | 21/07/2024 | 1
5 | Week 5: 22/07/24-28/07/24 | 22/07/2024 | 28/07/2024 | 5
5.1 | RQ1- Correlation Analysis | 22/07/2024 | 28/07/2024 | 5
5.2 | Quantify relationships between currency fluctuations | 23/07/2024 | 26/07/2024 | 4
5.3 | Quantify relationships between enrolment numbers | 23/07/2024 | 26/07/2024 | 4
5.4 | Quantify relationships between other variables | 23/07/2024 | 26/07/2024 | 4
5.5 | Quantify relationships between currency fluctuations, enrolment numbers, and other variables | 23/07/2024 | 26/07/2024 | 4
5.6 | Identify potential confounding factors. | 24/07/2024 | 27/07/2024 | 3
5.7 | Correlation matrix and analysis report | 28/07/2024 | 28/07/2024 | 1
6 | Week 6: 29/07/24- 4/08/24 | 29/07/2024 | 04/08/2024 | 5
6.1 | RQ2, RQ4 -Analysis of specific emerging market currencies and their impact on vulnerable student groups ( Data Week 4&5) | 29/07/2024 | 30/07/2024 | 2
6.2 | Begin conceptualising the forecast model: Research model types, identify data requirements. | 29/07/2024 | 30/07/2024 | 2
6.3 | RQ5- Examine the influence of demographic factors on the currency-enrolment relationship using regression | 31/07/2024 | 01/08/2024 | 2
6.4 | Continue model conceptualisation: Start preliminary data exploration and pre-processing for the model's dataset. | 31/07/2024 | 01/08/2024 | 2
6.5 | RQ6- Analysis of individual student characteristics and enrolment- Data (Week 4&5) | 02/08/2024 | 04/08/2024 | 1
6.6 | Start feature engineering for the model: Create additional variables or transformations. | 02/08/2024 | 04/08/2024 | 1
7 | Week 7: 5/08/24-11/08/24 | 05/08/2024 | 11/08/2024 | 5
7.1 | Model training and validation: Split data, build, and evaluate the model | 05/08/2024 | 06/08/2024 | 2
7.2 | Model selection: Compare different model types/configurations for optimal performance. | 07/08/2024 | 08/08/2024 | 2
7.3 | Refine model selection and potentially start model tuning | 09/08/2024 | 11/08/2024 | 1
7.4 | Complete any remaining in-depth analysis on RQ2, RQ4, RQ5, or RQ6 | 09/08/2024 | 11/08/2024 | 1
8 | Week 8: 12/08/24-18/08/24 | 12/08/2024 | 18/08/2024 | 5
8.1 | Finalise model tuning and optimisation | 12/08/2024 | 13/08/2024 | 2
8.2 | Generate enrolment forecasts based on expected currency changes | 12/08/2024 | 13/08/2024 | 2
8.3 | Interpret the model: Analyse coefficients and feature importance | 14/08/2024 | 15/08/2024 | 2
8.4 | Begin synthesising findings, draw insights and outline recommendations | 14/08/2024 | 15/08/2024 | 2
8.5 | Complete remaining dissertation chapters incorporating model results and findings | 15/08/2024 | 18/08/2024 | 2
8.6 | Create Poster Presentation and Critique project with peers and supervisor for final feedback | 15/08/2024 | 18/08/2024 | 2